📁 FILE 3 — Marketing Elements & Strategy Recommendations (Step 3)

1. PR Marketing

- Press release to national media (The Star, Bernama, Astro AWANI, Hype.my) announcing the biggest 11.11 sale in company history

- Media Preview Night (30 Oct): exclusive early-access showcase for journalists & editors, with interview slots for the Marketing Director

- CSR hook: UrbanMart donates 1% of all 11.11 sales to a local food bank — strong earned-media angle

- Estimated cost: RM 8,000 (venue, media kit, F&B, press release distribution)

2. Influencer Marketing

| Tier | Followers | Qty | Fee/Creator | Deliverables |
| --- | --- | --- | --- | --- |
| Macro/Celebrity | 500K+ | 1 | RM 15,000 | 2 reels + 1 TikTok LIVE shopping (Nov 11) |
| Mid-tier | 50K–250K | 4 | RM 4,000 | 1 reel + 3 stories w/ trackable codes |
| Micro | 10K–50K | 8 | RM 750 | 1 reel + stories |
| Nano | 1K–10K | 15 | RM 100 | Seeding + honest review posts |

Budget: RM 38,500 | Schedule: teasers 28–31 Oct → category takeovers Nov 2–6 → LIVE shopping party Nov 11, 8–11pm.

3. Billboard / Signboard Branding (OOH)

| Placement | Duration | Cost |
| --- | --- | --- |
| 2 highway static billboards (Federal Hwy, LDP) | 25 Oct – 15 Nov | RM 24,000 |
| 4 mall digital screens (Mid Valley, Sunway Pyramid, IOI, 1 Utama) | 1–11 Nov | RM 20,000 |
| 20 bus-stop panels near store catchments | 25 Oct – 15 Nov | RM 8,000 |
| In-store signboards, shelf talkers, standees | Full campaign | RM 6,000 |

Budget: RM 58,000 | Creative: "80% OFF. Need we say more? 1–11.11"

4. Digital Marketing — Ideas, Costing & Timeline

| Channel | Tactics | Ad Spend |
| --- | --- | --- |
| Meta (FB/IG) | Carousel catalogs, dynamic retargeting, story countdowns | RM 20,000 |
| TikTok | In-feed ads, TopView teaser, LIVE shopping boost | RM 12,000 |
| Google | Search ("11.11 sale Malaysia"), PMax, YouTube bumper ads | RM 10,000 |
| Marketplace | Shopee/Lazada on-platform search ads | RM 3,000 |
| CRM | Email + SMS + WhatsApp blasts (see File 4) | RM 2,500 |

Ad spend subtotal: RM 47,500

Campaign Timeline:

| Phase | Dates | Focus |
| --- | --- | --- |
| Tease | 20–31 Oct | Countdown content, VIP early access, influencer seeding |
| Launch | 1–7 Nov | Category spotlight days, heavy paid push |
| Peak | 8–11 Nov | Max budget delivery, hourly flash deal push, LIVE shopping |
| Retain | 12–17 Nov | Thank-you email, review requests, retargeting cart abandoners |

5. B2B Marketing Ideas (6 ideas)

- Corporate Bulk Purchase Program — tiered discounts (RM5K→10%, RM10K→20%, RM30K→30%, RM50K→40%) for offices buying electronics/pantry in bulk

- Corporate Gifting Packages — curated 11.11 hampers with company logo for year-end client/employee gifting

- Trade Partner Flash Stock — resellers get B2B pricing + priority stock reservation before public launch

- Office Supply Subscription Lock-In — sign a 6–12 month pantry/supplies contract during 11.11 at permanently discounted rates

- Employee Benefit Program — exclusive staff discount codes for corporate HR partners (they get perks; we get volume)

- B2B Buyer Preview Day — virtual showroom + dedicated account managers for procurement teams, 29–30 Oct

6. Pros & Cons of 3 Marketing Strategies

| Strategy | Pros | Cons |
| --- | --- | --- |
| Influencer Marketing | High trust & authenticity; precise audience targeting; fast content production; trackable via codes | Variable ROI; brand-safety risk; results fade quickly; pricing not standardized |
| Billboard / OOH | Massive mass reach; builds brand credibility; 24/7 visibility; great for urgent "sale is here" messaging | Expensive; no direct click-through; hard to measure conversion; fixed locations |
| Digital (Paid Social/Search) | Fully measurable ROI; precise targeting & retargeting; flexible budget scaling; drives direct sales | Ad fatigue; rising CPMs during 11.11 (all brands compete); requires constant optimization; ad-blocker loss |

7. Pop-Up Stalls & Customer Engagement

Concept: "The 11.11 Deal Zone" — 3 mall pop-ups (Mid Valley, Sunway Pyramid, IOI City Mall) + 1 campus activation, weekends of Nov 1–2, 8–9, and 11.

Engagement activities:

- 🎡 Spin-the-Wheel — win 11%–80% discount vouchers (every visitor)

- 🎁 RM11 Mystery Boxes — hourly drops at 11am & 11pm

- 📸 Giant 11.11 photo frame + hashtag contest — post with #UrbanMart1111 to win a RM1,111 shopping spree

- 🛍️ First 111 visitors daily get a free gift

- 📲 QR-scan membership sign-up = instant RM20 voucher (data capture!)

Cost estimate: RM 34,000 (rental RM15K, booth fabrication RM12K, staffing RM6K, giveaways RM1K)