📁 FILE 5 — Agency Costing Report / Proposal (Step 5)

To: UrbanMart Retail Sdn. Bhd. | From: [Agency Name] | Date: [Date] | Validity: 14 days

A. Agency Professional Fees

| Service | Details | Fee (RM) |
| --- | --- | --- |
| Campaign strategy & planning | Full 11.11 master plan, channel strategy, timeline | 6,500 |
| Creative development | Key visual, 5 social posters, 4 website banners + adaptations | 9,000 |
| Copywriting | 5 email contents, captions, press release, OOH copy | 3,500 |
| Digital ad setup & management | 6 weeks: audience building, creative rotation, daily optimization | 7,500 |
| Influencer sourcing & management | Contracts, briefs, content review, reporting | 4,500 |
| Pop-up stall design & PM | Booth concept, fabrication liaison, staffing coordination | 5,500 |
| Email marketing setup | Templates, automation flows, segmentation | 2,500 |
| Reporting & analytics | Weekly dashboards + final campaign report | 2,000 |
| Subtotal (A) |  | 41,000 |

B. Third-Party / Media Costs (pass-through, at cost)

| Item | Amount (RM) |
| --- | --- |
| Digital ad spend (Meta/TikTok/Google/Marketplace) | 47,500 |
| Influencer fees (28 creators) | 38,500 |
| OOH: billboards, digital screens, bus panels | 52,000 |
| Pop-up stalls (rental, fabrication, staffing, giveaways) | 34,000 |
| PR launch event & media kits | 8,000 |
| Printing & in-store materials | 6,000 |
| Subtotal (B) | 186,000 |

C. Total Investment Summary

|  | Amount (RM) |
| --- | --- |
| A. Agency Fees | 41,000 |
| B. Third-Party Costs | 186,000 |
| Contingency (5%, optional) | 11,350 |
| TOTAL CAMPAIGN BUDGET | RM 238,350 |

Projected ROI: campaign revenue target RM 2.5M ≈ 10.5x return on total marketing spend.

Payment Terms

- 50% (RM 119,175) upon signing — mobilization & media bookings

- 40% (RM 95,340) on 1 Nov — campaign launch

- 10% (RM 23,835) within 14 days of final report

Terms & Conditions

- Media bookings made on client's behalf are non-refundable after 20 Oct 2025.

- Ad spend overruns above 110% of budget require written client approval.

- All creative assets delivered become client property upon final payment.

- Rates exclude applicable SST/taxes.

- Influencer deliverables guaranteed per contract; one (1) replacement cycle included.